## Sheet1
Requirements Tracebility Matrix
| Project Name: |  |  |  | Author Name:
Req # unique Id | Requirement Name/Description | Requested / Approved by | Scope Deliverable / Feature: | Scope # Unique ID: | User story or Work Package | Assigned to | Test Case | Current Status
REQ001 | Implement biometric login | Project Manager | Biometric Authentication | SCOPE001 | As a user, I want to log in using my fingerprint | John Doe | TC001 | Complete
REQ002 | Enable facial recognition | Product Owner | Biometric Authentication | SCOPE001 | As a user, I want to log in using facial recognition | Jane Smith | TC002 | Testing
REQ003 | Create user profile for biometrics | Product Owner | User Management | SCOPE002 | As an admin, I want to create user profiles with biometric data | Mike Johnson | TC003 | Complete
REQ004 | Implement expense input | Project Manager | Expenditure Tracking | SCOPE003 | As a user, I want to manually input my expenses | Sarah Lee | TC004 | Development
REQ005 | Categorize expenses automatically | Product Owner | Expenditure Tracking | SCOPE003 | As a user, I want my expenses to be automatically categorized | Tom Brown | TC005 | Elaboration
REQ006 | Generate monthly expense reports | Product Owner | Reporting | SCOPE004 | As a user, I want to generate monthly expense reports | Lisa Chen | TC006 | Not Started
REQ007 | Integrate with bank accounts | Project Manager | Data Integration | SCOPE005 | As a user, I want my bank transactions to be automatically tracked | John Doe | TC007 | Development
REQ008 | Implement data encryption | Project Manager | Security | SCOPE006 | As a system, I want to encrypt all user data | Jane Smith | TC008 | Complete
REQ009 | Create user dashboard | Product Owner | User Interface | SCOPE007 | As a user, I want a dashboard to view my expense overview | Mike Johnson | TC009 | Testing
REQ010 | Enable multi-factor authentication | Product Owner | Security | SCOPE006 | As a user, I want to use MFA for additional security | Sarah Lee | TC010 | Elaboration
REQ011 | Implement budget setting feature | Project Manager | Financial Planning | SCOPE008 | As a user, I want to set monthly budgets for different categories | Tom Brown | TC011 | Not Started
REQ012 | Create expense sharing functionality | Product Owner | Collaboration | SCOPE009 | As a user, I want to share expenses with other users | Lisa Chen | TC012 | Development

## Sheet2
Statuses
Not Started
Elaboration
Development
Testing
Complete
Released
This RTM captures the key requirements for your biometric login and expenditure tracking project, aligning with the information you provided. It includes a mix of features related to biometric authentication, expense tracking, security, and user interface elements. The statuses reflect various stages of development, from "Not Started" to "Complete," which allows for tracking progress throughout the Agile Scrum process.
Share
Rewrite